## Consolidated
Consolidated | Tasks | Time (h)
| Playback from MP3 file | 1
| Style playback with duration bar, play/pause button, etc | 1.5
| Get JSON blob from API describing ad timestamps | 0.5
| Add button to track state between ad skipped and not skipped | 0.25
| If skiping, check if we're in an ad and if so skip playback head to end of ad timestamp | 1
| If not skipping, don't do that ^^ | 0.2
| Handle what should happen if the user enables skipping while an ad is already in progress | 0.5
| Save skip/don't skip preference to DB | 0.5
| Check saved preference at beginning of playback session on each device | 0.25
| Edit displayed duration to subtract out ad duration from displayed duration when adblock is active | 1
| Indicate toggle | 0.2
| Total | 6.9

## Ezra
User Story 3 | Tasks | Time (h)
| Playback from MP3 file | 1.5
| Style playback with duration bar, play/pause button, etc | 2.5
| Get JSON blob from API describing ad timestamps | 0.5
| Add button to track state between ad skipped and not skipped | 0.5
| If skiping, check if we're in an ad and if so skip playback head to end of ad timestamp | 1
| If not skipping, don't do that ^^ | 0.2
| Handle what should happen if the user enables skipping while an ad is already in progress | 0.5
| Save skip/don't skip preference to DB | 0.5
| Check saved preference at beginning of playback session on each device | 0.5
| Edit displayed duration to subtract out ad duration from displayed duration when adblock is active | 1.5
| Total | 9.2

## John
Task: | As a logged in user playing a podcast, I want to be able to press a button to toggle between listening with adblock enabled and disabled.
List:
1. Build a audio playback and adblock functionality |  | 0.5
2. Have a user preference functionality that allows to toggle |  | 0.25
3. Storeuser preferences in the database |  | 0
4. Have an MP3 Player that allows to play the Podcasts |  | 0.25
5. Have an oauth system so that only authenticated users can use this functionality |  | 0.5
6. Create a Button for the user to toggle this preference |  | 0
7. Implement the logic for adblock |  | 2.5
8. Have a backend api for the toggle |  | 0.5
9. Have a simple message/signal that indicates for the toggle |  | 0
Total |  | 4.5